## All Country Tabs
FY23 Workplans
Anguilla
Antigua and Barbuda
Aruba
Bahamas
Barbados
Belize
Bermuda
British Virgin Islands
Cayman Islands
Curacao
Dominica
ECCB
Grenada
Guyana
Haiti
Jamaica
Montserrat
Sint Maarten
St Kitts and Nevis
St Lucia
St Vincent and the Grenadines
Suriname
Trinidad and Tobago
Turks and Caicos
Regional Training

## Anguilla
CARTAC FY23 Workplan - Anguilla
Work Program | Activity Name | CD Modality | Start Date | End Date
Customs Administration | Strengthening Performance Management | Duty station-based Work - DS | 2022-07-11 | 2022-07-15
Customs Administration | Legal - Drafting of New Law for Customs | Field-Based work - FB | 2022-09-05 | 2022-09-05
Customs Administration | Strengthening Performance Management | Field-Based work - FB | 2023-04-17 | 2023-04-17
Financial and Fiscal Law | Legal - Drafting of New Law for Customs | Field-Based work - FB | 2022-09-05 | 2022-09-16
Financial and Fiscal Law | Strengthening Performance Management | Field-Based work - FB | 2023-04-17 | 2023-04-28
Macroeconomic Program | Anguilla-Macroeconomic programming and analysis | Duty station-based Work - DS | 2022-07-05 | 2022-07-08
Public Finance Management | Mission LTX/STX - PEFA Follow Up - Updated PFM Reform Action Plan FY23 | Duty station-based Work - DS | 2022-05-02 | 2022-05-27
Public Finance Management | Mission LTX/STX STRENGTHEN BUDGET PLANNING AND PREPARATION FY23 | Field-Based work - FB | 2022-06-06 | 2022-06-17
Tax Administration | Capacity Building - core functions - Taxpayer Services | Field-Based work - FB | 2022-06-01 | 2022-06-30
Tax Administration | LTX Follow up | Field-Based work - FB | 2022-08-08 | 2022-08-12
Tax Administration | Capacity Building - core functions | Duty station-based Work - DS | 2022-11-07 | 2022-11-22
Source: CARTAC

## Antigua and Barbuda
CARTAC FY23 Workplan - Antigua and Barbuda
Work Program | Activity Name | CD Modality | Start Date | End Date
External Sector Statistics | Antigua and Barbuda – TA – BOP – Source Data | Field-Based work - FB | 2022-08-08 | 2022-08-12
Real Sector Statistics | Antigua and Barbuda - TA -PPI - Updating SPPIs | Field-Based work - FB | 2022-10-17 | 2022-10-28
Real Sector Statistics | Antigua and Barbuda - TA - GDP - Improving GDP | Field-Based work - FB | 2023-02-06 | 2023-02-17
Tax Administration | Developing a compliance program for large taxpayers | Field-Based work - FB | 2022-09-28 | 2022-10-12
Tax Administration | LTX Visit | Field-Based work - FB | 2022-11-08 | 2022-11-11
Source: CARTAC

## Aruba
CARTAC FY23 Workplan - Aruba
Work Program | Activity Name | CD Modality | Start Date | End Date
Customs Administration | Strengthening Performance Management | Duty station-based Work - DS | 2022-10-24 | 2022-10-28
Customs Administration | Strengthening Performance Management | Field-Based work - FB | 2023-03-13 | 2023-03-24
External Sector Statistics | Aruba – TA – Develop QIIP and Compile SPE Data Template | Field-Based work - FB | 2022-08-29 | 2022-09-09
Financial Sector Supervision | Scoping Mission -LTX | Field-Based work - FB | 2022-08-15 | 2022-08-19
Financial Sector Supervision | Strengthening Off-site and On-site Supervision-STX | Field-Based work - FB | 2022-10-05 | 2022-10-24
Financial Stability | Aruba - Systemic Risk Analysis | Field-Based work - FB | 2022-08-01 | 2022-08-09
Public Finance Management | Mission LTX: Strengthening country engagement in PFM reform FY23 | Field-Based work - FB | 2022-06-20 | 2022-06-22
Public Finance Management | Mission LTX/STX Treasury scoping mission and development of Action Plan FY23 | Field-Based work - FB | 2023-04-03 | 2023-04-21
Tax Administration | Strengthening Core Business Functions - Audit Programme and CD | Field-Based work - FB | 2022-05-02 | 2022-05-02
Tax Administration | Strengthening Strategic Management Framework | Field-Based work - FB | 2022-07-01 | 2022-07-22
Tax Administration | LTX Visit | Field-Based work - FB | 2022-07-20 | 2022-07-22
Source: CARTAC

## Bahamas
CARTAC FY23 Workplan - The Bahamas
Work Program | Activity Name | CD Modality | Start Date | End Date
Debt Management | BHS CARTAC Nov FY23 Debt management strategy and annual borrowing plan (mission) | Field-Based work - FB | 2022-11-07 | 2022-11-18
External Sector Statistics | The Bahamas – TA – BOP/IIP – Enhance Consistency | Field-Based work - FB | 2023-02-13 | 2023-02-24
Macroeconomic Program | Bahamas FP2.0 Mission 4 | Duty station-based Work - DS | 2022-06-21 | 2022-06-24
Macroeconomic Program | Bahamas FP2.0 Mission 5 | Duty station-based Work - DS | 2022-10-25 | 2022-10-31
Macroeconomic Program | Bahamas FP2.0 Mission 6 | Duty station-based Work - DS | 2022-12-08 | 2022-12-15
Public Finance Management | Mission LTX/STX Support to medium term budgeting FY23 | Field-Based work - FB | 2022-11-07 | 2022-11-18
Real Sector Statistics | Bahamas, The - TA - GDP - Improving GDP FY23 | Field-Based work - FB | 2022-08-22 | 2022-09-02
Real Sector Statistics | Bahamas, The - TA - CPI - Updating CPI FY23 | Field-Based work - FB | 2022-09-05 | 2022-09-16
Tax Administration | Developing Institutional Risk Framework | Field-Based work - FB | 2022-05-02 | 2022-05-02
Tax Administration | TADAT Pre Assessment Training | Field-Based work - FB | 2022-09-01 | 2022-09-15
Source: CARTAC

## Barbados
CARTAC FY23 Workplan - Barbados
Work Program | Activity Name | CD Modality | Start Date | End Date
Customs Administration | Customs Cargo Clearance and Traceability | Field-Based work - FB | 2022-06-06 | 2022-06-17
Customs Administration | Customs - Valuation administrative policy suite and valuation audit | Field-Based work - FB | 2022-10-10 | 2022-10-21
Customs Administration | Strengthening Risk Management Capacity/Strengthening the Trusted Trader Program | Duty station-based Work - DS | 2022-11-28 | 2022-12-02
Customs Administration | Strengthening Risk Management Capacity/Strengthening the Trusted Trader Program 2 | Duty station-based Work - DS | 2023-02-06 | 2023-02-10
Debt Management | BRB CARTAC Feb FY23 Debt market development (mission) | Field-Based work - FB | 2023-02-06 | 2023-02-17
External Sector Statistics | Barbados – TA – CPIS/CDIS – Improve Timeliness | Field-Based work - FB | 2022-10-03 | 2022-10-07
Financial Sector Supervision | TA on the Supervision of Credit Bureau -STX | Field-Based work - FB | 2022-09-07 | 2022-09-19
Financial Sector Supervision | Workshop on Supervision of Climate Risk | Field-Based work - FB | 2022-10-12 | 2022-10-24
Financial Sector Supervision | Workshop - Supervisory Review of Cyber Risk Management at FIs -STX | Field-Based work - FB | 2022-11-09 | 2022-11-21
Financial Sector Supervision | Workshop on Climate Risk Supervision - STX | Field-Based work - FB | 2022-11-30 | 2022-12-12
Financial Sector Supervision | Workshop on Sup Framework for Cyber Risk and Fintech Firms -STX | Field-Based work - FB | 2023-03-01 | 2023-03-13
Financial Stability | BRB CARTAC 2023 FSR | Field-Based work - FB | 2022-09-05 | 2022-09-09
Macroeconomic Program | #CC Building capacity in medium term macro-fiscal frameworks | Duty station-based Work - DS | 2022-05-30 | 2022-06-02
Macroeconomic Program | #CC Building capacity in medium term macroeconomic framework | Field-Based work - FB | 2022-09-26 | 2022-09-30
Public Finance Management | Mission LTX/STX Review of Cashflow Model and Training FY23 | Duty station-based Work - DS | 2022-05-09 | 2022-05-23
Public Finance Management | Mission LTX/STX Review of Treasury to include establishing the Cash Management Unit FY23 | Duty station-based Work - DS | 2022-05-09 | 2022-06-03
Public Finance Management | Mission LTX/STX Development of Fiscal framework FY23 | Field-Based work - FB | 2022-06-06 | 2022-06-17
Public Finance Management | Mission LTX/STX Review of Budget Process and Procedures FY23 | Field-Based work - FB | 2022-09-19 | 2022-09-30
Public Finance Management | Mission LTX/STX Treasury Function Reform FY23 | Field-Based work - FB | 2022-11-07 | 2022-11-18
Public Finance Management | Mission LTX/STX – Follow-up assistance with IA FY23 | Field-Based work - FB | 2023-01-09 | 2023-01-13
Real Sector Statistics | Barbados - TA - GDP - Improving GDP FY23 | Field-Based work - FB | 2023-02-06 | 2023-02-10
Tax Administration | Organizational Arrangements - Compliance Risk Management Unit | Duty station-based Work - DS | 2022-06-13 | 2022-07-01
Tax Administration | Enhancing Compliance Programs | Field-Based work - FB | 2022-10-03 | 2022-10-21
Source: CARTAC

## Belize
CARTAC FY23 Workplan - Belize
Work Program | Activity Name | CD Modality | Start Date | End Date
Customs Administration | Merger of different tax departments | Field-Based work - FB | 2022-09-16 | 2022-09-16
Customs Administration | Strengthening Performance Management | Field-Based work - FB | 2022-10-10 | 2022-10-21
Financial Sector Supervision | RBS Implementation (Follow-up) - LTX | Duty station-based Work - DS | 2022-05-11 | 2022-05-23
Financial Sector Supervision | Basel II-III - Implementation of LCR (Follow-up) - STX | Duty station-based Work - DS | 2022-07-07 | 2022-07-15
Financial Sector Supervision | Scoping Mission -LTX | Field-Based work - FB | 2022-09-12 | 2022-09-16
Financial Sector Supervision | Development of Liquidity and Capital Standards for Registrants - STX | Field-Based work - FB | 2022-10-12 | 2022-11-23
Financial Sector Supervision | Basel II-III - Implementation of Capital Buffers -STX | Field-Based work - FB | 2022-10-12 | 2022-10-24
Financial Sector Supervision | RBS Implementation (Follow-up) -STX | Field-Based work - FB | 2022-11-02 | 2022-11-14
Financial Stability | BEL CARTAC Apr 2022 Macro stress testing | Duty station-based Work - DS | 2022-05-11 | 2022-06-14
Public Finance Management | Mission HQ/LTX/STX Accruals Accounting Implementation Plan FY23 | Field-Based work - FB | 2022-09-26 | 2022-09-30
Public Finance Management | Mission LTX/STX – Improving Treasury reporting function FY23 | Field-Based work - FB | 2023-01-09 | 2023-01-20
Real Sector Statistics | Belize - TA - CPI - Updating CPI | Field-Based work - FB | 2023-02-06 | 2023-02-17
Tax Administration | Merger of different tax departments | Field-Based work - FB | 2022-08-29 | 2022-09-16
Tax Administration | LTX Visit | Field-Based work - FB | 2022-10-05 | 2022-10-07
Tax Administration | Strengthening Core Business function | Duty station-based Work - DS | 2022-11-07 | 2022-11-18
Tax Administration | Strengthening HQ function and performance management | Field-Based work - FB | 2023-02-06 | 2023-02-15
Source: CARTAC

## Bermuda
CARTAC FY23 Workplan - Bermuda
Work Program | Activity Name | CD Modality | Start Date | End Date
External Sector Statistics | Bermuda – BOP/IIP/CPIS – Enhance coverage | Field-Based work - FB | 2022-08-22 | 2022-08-31
Macroeconomic Program | Mission Strengthening country engagement in PFM reform FY23 | Field-Based work - FB | 2022-06-13 | 2022-06-15
Public Finance Management | Mission Strengthening country engagement in PFM reform FY23 | Field-Based work - FB | 2022-06-13 | 2022-06-15
Real Sector Statistics | Bermuda - TA - CPI - Updating CPI | Duty station-based Work - DS | 2022-06-06 | 2022-06-17
Source: CARTAC

## BVI
CARTAC FY23 Workplan - British Virgin Islands
Work Program | Activity Name | CD Modality | Start Date | End Date
External Sector Statistics | British Virgin Islands – BOP – Source Data | Field-Based work - FB | 2023-02-13 | 2023-02-24
Macroeconomic Program | British Virgin Islands-Macroeconomic programming and analysis | Field-Based work - FB | 2022-06-07 | 2022-06-08
Macroeconomic Program | Mission LTX Strengthening country engagement in PFM reform FY23 | Field-Based work - FB | 2022-06-20 | 2022-06-22
Macroeconomic Program | Building capacity in medium-term macro frameworks | Field-Based work - FB | 2022-10-24 | 2022-10-28
Public Finance Management | Mission LTX Strengthening country engagement in PFM reform FY23 | Field-Based work - FB | 2022-06-20 | 2022-06-22
Real Sector Statistics | British Virgin Islands - TA - GDP - Improving GDP | Duty station-based Work - DS | 2022-07-25 | 2022-08-05
Tax Administration | LTX Visit | Field-Based work - FB | 2022-08-24 | 2022-08-26
Tax Administration | Strengthen organizational arrangements | Field-Based work - FB | 2022-09-05 | 2022-09-16
Source: CARTAC

## Cayman Islands
CARTAC FY23 Workplan - Cayman Islands
Work Program | Activity Name | CD Modality | Start Date | End Date
Customs Administration | Strengthening Risk Management | Field-Based work - FB | 2022-05-16 | 2022-05-27
Customs Administration | Strengthening Performance Management | Field-Based work - FB | 2023-04-03 | 2023-04-07
External Sector Statistics | Cayman Islands - TA - BOP - Improve Coverage and Compile SPE Data Template | Field-Based work - FB | 2022-10-17 | 2022-10-28
Financial Stability | CARTAC FY23 MacroPrudential | Field-Based work - FB | 2023-02-06 | 2023-02-10
Financial Stability | Cayman Islands-Systemic Risk and Financial Stability | Peer-to-peer engagement - PP | 2023-04-03 | 2023-04-05
Real Sector Statistics | Cayman Islands - TA - GDP - Improving GDP | Field-Based work - FB | 2022-11-14 | 2022-11-25
Source: CARTAC

## Curacao
CARTAC FY23 Workplan - Curacao
Work Program | Activity Name | CD Modality | Start Date | End Date
External Sector Statistics | Curaçao and Sint Maarten – TA – IIP – Enhance Data Sources | Field-Based work - FB | 2023-01-16 | 2023-01-27
Financial Sector Supervision | RBS Implementation -Follow-up - LTX | Field-Based work - FB | 2022-08-17 | 2022-08-29
Financial Sector Supervision | Scoping Mission -LTX | Field-Based work - FB | 2022-10-10 | 2022-10-14
Financial Sector Supervision | RBS Implementation - Follow-up - STX | Field-Based work - FB | 2022-11-30 | 2022-12-12
Financial Sector Supervision | Basel II-III Pillar 2 Implementation (Follow-up) STX | Field-Based work - FB | 2023-03-15 | 2023-03-27
Financial Stability | CUR CARTAC FY23 FSR writing | Field-Based work - FB | 2023-02-06 | 2023-02-10
Financial Stability | CUR CARTAC FY23 Monitoring systemic risk | Field-Based work - FB | 2023-04-03 | 2023-04-07
Macroeconomic Program | Curacao-Macroeconomic programming and analysis | Duty station-based Work - DS | 2022-05-10 | 2022-11-25
Public Finance Management | Mission LTX: Strengthening country engagement in PFM reform FY23 | Field-Based work - FB | 2022-06-22 | 2022-06-24
Source: CARTAC

## Dominica
CARTAC FY23 Workplan - Dominica
Work Program | Activity Name | CD Modality | Start Date | End Date
External Sector Statistics | Dominica - TA - BOP - Source Data | Field-Based work - FB | 2022-07-23 | 2022-10-25
Public Finance Management | Mission LTX/STX Green/Gender budgeting FY23 #cc #gender | Field-Based work - FB | 2022-09-05 | 2022-09-16
Real Sector Statistics | Dominica - TA - GDP - Improving GDP | Field-Based work - FB | 2022-10-03 | 2022-10-14
Tax Administration | Strengthening Audit Capacity - Training in Audit Computer Audit Techniques | Duty station-based Work - DS | 2022-05-02 | 2022-05-31
Tax Administration | Strengthening Core Business Functions - Audit Capacity (RTAT) | Duty station-based Work - DS | 2022-08-01 | 2022-08-11
Tax Administration | LTX Visit | Field-Based work - FB | 2023-01-18 | 2023-02-07
Source: CARTAC

## ECCB
CARTAC FY23 Workplan - Eastern Caribbean Central Bank
Work Program | Activity Name | CD Modality | Start Date | End Date
External Sector Statistics | Eastern Caribbean Central Bank – TA – BOP/IIP – Develop Quarterly Data | Field-Based work - FB | 2022-12-05 | 2022-12-16
External Sector Statistics | Eastern Caribbean Central Bank-TA-BOP/IIP-Anguilla | Field-Based work - FB | 2023-01-16 | 2023-01-20
External Sector Statistics | Eastern Caribbean Central Bank-TA-BOP/IIP-Montserrat | Field-Based work - FB | 2023-01-30 | 2023-02-03
Financial Sector Supervision | Scoping Mission -LTX | Field-Based work - FB | 2022-09-05 | 2022-09-09
Financial Sector Supervision | TA on Review of Prudential Standards and LCR | Field-Based work - FB | 2022-09-12 | 2022-09-23
Financial Stability | ECCB CARTAC Stress test | Duty station-based Work - DS | 2022-10-03 | 2022-10-07
Macroeconomic Program | ECCU - TA - Eastern Caribbean Central Bank | Duty station-based Work - DS | 2022-09-05 | 2022-09-09
Macroeconomic Program | ECCU/ECCB follow-up on DDT implementation | Field-Based work - FB | 2022-10-10 | 2022-10-14
Macroeconomic Program | ECCU - TA - Eastern Caribbean Central Bank | Field-Based work - FB | 2022-12-05 | 2022-12-09
Macroeconomic Program | FY23 Scoping Mission | Duty station-based Work - DS | 2023-03-06 | 2023-03-09
Macroeconomic Program | ECCU - TA - Eastern Caribbean Central Bank | Field-Based work - FB | 2023-04-03 | 2023-04-07
Debt Management | ECCB CARTAC Aug FY23 Regional government securities market (mission) | Field-Based work - FB | 2022-08-01 | 2022-08-12
Source: CARTAC

## Grenada
CARTAC FY23 Workplan - Grenada
Work Program | Activity Name | CD Modality | Start Date | End Date
Customs Administration | Review of Workload/Resource Allocation | Field-Based work - FB | 2022-09-12 | 2022-09-23
Customs Administration | Strengthening Performance Management | Duty station-based Work - DS | 2022-11-28 | 2022-12-02
Customs Administration | Review of Workload/Resource Allocation | Duty station-based Work - DS | 2023-01-30 | 2023-02-03
Customs Administration | Strengthening Performance Management | Field-Based work - FB | 2023-03-13 | 2023-03-24
External Sector Statistics | Grenada – TA – BOP – Develop Quarterly Data | Field-Based work - FB | 2022-11-07 | 2022-11-11
Financial Sector Supervision | RBS Implementation (Follow-up) - STX | Field-Based work - FB | 2023-03-01 | 2023-03-10
Public Finance Management | Mission LTX/STX Strengthening oversight of SOEs FY23 | Field-Based work - FB | 2023-04-10 | 2023-04-21
Tax Administration | Strengthening Core Business function | Field-Based work - FB | 2022-05-02 | 2022-05-02
Tax Administration | Strengthening Core Business function - Arrears Management | Duty station-based Work - DS | 2022-07-01 | 2022-08-01
Tax Administration | LTX Visit | Field-Based work - FB | 2022-11-01 | 2022-11-03
Source: CARTAC

## Guyana
CARTAC FY23 Workplan - Guyana
Work Program | Activity Name | CD Modality | Start Date | End Date
Customs Administration | Strengthening Analytical Capacity | Field-Based work - FB | 2022-06-13 | 2022-06-24
Customs Administration | Strengthening Performance Management | Duty station-based Work - DS | 2022-07-18 | 2022-07-22
Customs Administration | Developing the Trusted Trader Program/AEO | Field-Based work - FB | 2022-09-26 | 2022-09-26
Customs Administration | Strengthening Analytical Capacity | Field-Based work - FB | 2023-01-09 | 2023-01-09
Customs Administration | Strengthening Performance Management | Field-Based work - FB | 2023-02-27 | 2023-03-03
Customs Administration | Developing the Trusted Trader Program/AEO | Duty station-based Work - DS | 2023-03-13 | 2023-03-13
External Sector Statistics | Guyana – TA – BOP/IIP – Enhance Data Sources | Field-Based work - FB | 2023-03-20 | 2023-03-31
Financial Sector Supervision | Scoping Mission -LTX | Field-Based work - FB | 2022-07-11 | 2022-07-15
Financial Sector Supervision | Basel II-III Implementation - Pillar 2 (Follow-up) -STX | Field-Based work - FB | 2022-10-12 | 2022-10-25
Public Finance Management | Mission LTX/STX Strengthening Cash Management FY23 | Field-Based work - FB | 2023-01-25 | 2023-01-31
Real Sector Statistics | Guyana - TA - GDP - Improving GDP FY23 | Field-Based work - FB | 2022-06-06 | 2022-06-17
Tax Administration | Strengthening Core Business Functions - Audit of Financial Institutions | Field-Based work - FB | 2022-09-05 | 2022-09-16
Tax Administration | Strengthening Core Business Functions - Audit of Insurance Companies | Field-Based work - FB | 2022-11-07 | 2022-11-18
Source: CARTAC

## Haiti
CARTAC FY23 Workplan - Haiti
Work Program | Activity Name | CD Modality | Start Date | End Date
Debt Management | CARTAC Oct FY23 Market development (mission) | Duty station-based Work - DS | 2022-10-03 | 2022-10-14
External Sector Statistics | TA – BOP/IIP - Address Data Gaps | Duty station-based Work - DS | 2022-06-06 | 2022-06-17
Macroeconomic Program | FP2.0 scoping TA mission | Field-Based work - FB | 2022-10-10 | 2022-10-14
Macroeconomic Program | FP2.0 remote training 1 | Duty station-based Work - DS | 2023-02-06 | 2023-02-17
Macroeconomic Program | Macroeconomic Frameworks TA—Ministry of Finance | Duty station-based Work - DS | 2023-04-17 | 2023-04-21
Public Finance Management | Mission LTX/STX Improvements in Budget Planning (Training) FY23 | Duty station-based Work - DS | 2022-12-05 | 2022-12-09
Real Sector Statistics | TA - RPPI - Developing RPPI FY23 | Field-Based work - FB | 2022-11-07 | 2022-11-18
Real Sector Statistics | TA - CPI - Updating CPI | Field-Based work - FB | 2023-01-09 | 2023-01-20
Source: CARTAC

## Jamaica
CARTAC FY23 Workplan - Jamaica
Work Program | Activity Name | CD Modality | Start Date | End Date
Debt Management | Government debt market (mission) | Field-Based work - FB | 2023-04-03 | 2023-04-14
External Sector Statistics | TA - BOP/IIP - Enhance Source Data | Field-Based work - FB | 2023-01-30 | 2023-02-10
Financial Sector Supervision | Basel II-III_ Capital Buffers and DSIB Surcharge - STX | Duty station-based Work - DS | 2022-09-12 | 2022-09-19
Financial Sector Supervision | Scoping Mission - LTX | Field-Based work - FB | 2022-09-19 | 2022-09-23
Financial Sector Supervision | Basel II-III Implementation - Follow-up TA Pillar 2 (ICAAP)-STX | Duty station-based Work - DS | 2022-10-17 | 2022-10-27
Financial Sector Supervision | Cyber Risk - Regulatory and Supervisory Framework - STX | Duty station-based Work - DS | 2022-11-14 | 2022-11-30
Financial Sector Supervision | Basel II-III_ Pillar 2 (SRP) - STX | Field-Based work - FB | 2023-01-04 | 2023-01-13
Financial Sector Supervision | Review of Draft RM Guidance and Drafting of ORSA LM Guidelines -STX | Duty station-based Work - DS | 2023-02-01 | 2023-02-22
Financial Sector Supervision | Basel II-III - Supervisory Review of Bottom-up ST and Scenario Analysis -STX | Field-Based work - FB | 2023-03-20 | 2023-03-30
Financial Stability | FY23 Macro-financial forecast | Field-Based work - FB | 2022-11-07 | 2022-11-11
Financial Stability | Systemic Risk and Financial Stability | Duty station-based Work - DS | 2023-02-06 | 2023-02-10
Financial Stability | Systemic Risk and Financial Stability | Peer-to-peer engagement - PP | 2023-04-03 | 2023-04-05
Macroeconomic Program | Virtual delivery - MTF third development mission | Duty station-based Work - DS | 2022-05-27 | 2022-06-17
Macroeconomic Program | MFT 4th delivery | Duty station-based Work - DS | 2022-09-05 | 2022-09-09
Macroeconomic Program | MFT 5th delivery | Field-Based work - FB | 2022-10-10 | 2022-10-14
Macroeconomic Program | MFT 6th delivery | Field-Based work - FB | 2023-02-06 | 2023-02-10
Public Finance Management | Mission LTX Strengthening country engagement in PFM reform | Field-Based work - FB | 2022-06-06 | 2022-06-08
Real Sector Statistics | TA - GDP - Improving GDP | Field-Based work - FB | 2022-10-03 | 2022-10-14
Tax Administration | Corporate Priorities better managed - Strengthening institutional framework | Duty station-based Work - DS | 2022-05-02 | 2022-05-02
Tax Administration | Post TADAT mission | Field-Based work - FB | 2022-05-13 | 2022-05-27
Tax Administration | Corporate Priorities better managed - Business Impact Analysis | Duty station-based Work - DS | 2022-05-20 | 2022-06-20
Tax Administration | LTX - Visit | Field-Based work - FB | 2022-07-11 | 2022-07-15
Source: CARTAC

## Montserrat
CARTAC FY23 Workplan - Montserrat
Work Program | Activity Name | CD Modality | Start Date | End Date
Public Finance Management | Mission LTX/STX STRENGTHEN BUDGET PLANNING AND PREPARATION FY23 | Duty station-based Work - DS | 2022-05-02 | 2022-05-31
Public Finance Management | Mission LTX/STX– FY23 Chart of Accounts Support FY23 | Field-Based work - FB | 2022-06-13 | 2022-06-17
Public Finance Management | Mission LTX/STX Internal Audit Support to Audit Committee FY23 | Field-Based work - FB | 2022-09-05 | 2022-09-09
Tax Administration | Strengthening Organizational Arrangements | Field-Based work - FB | 2022-07-18 | 2022-07-28
Tax Administration | Strengthening Core Business Functions - Arrears Management | Duty station-based Work - DS | 2022-08-15 | 2022-08-30
Tax Administration | LTX Visit | Field-Based work - FB | 2022-11-01 | 2022-11-04
Source: CARTAC

## St Maarten
CARTAC FY23 Workplan - Sint Maarten
Work Program | Activity Name | CD Modality | Start Date | End Date
Macroeconomic Program | Building capacity in medium-term macro framework | Duty station-based Work - DS | 2022-06-06 | 2022-06-10
Macroeconomic Program | St Maarten: Developing Macroeconomic and Fiscal Analytical Capacity | Field-Based work - FB | 2023-04-10 | 2023-04-14
Public Finance Management | Strengthening medium term budget planning FY23 | Field-Based work - FB | 2023-02-06 | 2023-02-17
Real Sector Statistics | Sint Maarten Kingdom of the Netherlands - TA - GDP - Improving GDP | Field-Based work - FB | 2023-01-09 | 2023-01-20
Tax Administration | Strengthening Core Business Function - Arrears Management | Field-Based work - FB | 2022-07-04 | 2022-07-18
Tax Administration | Strengthening Core Business Function - Audit Capacity | Duty station-based Work - DS | 2022-09-05 | 2022-09-19
Tax Administration | LTX Visit | Field-Based work - FB | 2023-01-09 | 2023-01-11
Source: CARTAC

## St Kitts and Nevis
CARTAC FY23 Workplan - St Kitts and Nevis
Work Program | Activity Name | CD Modality | Start Date | End Date
External Sector Statistics | TA – BOP – Develop Quarterly BOP Statement | Field-Based work - FB | 2022-09-12 | 2022-09-16
Public Finance Management | Agile PEFA Assessment FY23 #cc #gender | Field-Based work - FB | 2022-09-05 | 2022-09-16
Real Sector Statistics | TA - CPI - Updating CPI | Field-Based work - FB | 2022-12-05 | 2022-12-16
Real Sector Statistics | TA - GDP - Improving GDP FY23 | Field-Based work - FB | 2023-04-10 | 2023-04-21
Tax Administration | Strengthening HQ function (Peer to Peer engagement with Grenada) | Peer-to-peer engagement - PP | 2022-06-06 | 2022-06-10
Tax Administration | LTX VISIT | Field-Based work - FB | 2022-09-26 | 2022-09-29
Tax Administration | Strengthening Compliance Program - VAT and Income Tax Cross Matching | Field-Based work - FB | 2022-10-03 | 2022-10-21
Source: CARTAC

## St Lucia
CARTAC FY23 Workplan - St Lucia
Work Program | Activity Name | CD Modality | Start Date | End Date
External Sector Statistics | BOP/IIP – Compile QBOP | Field-Based work - FB | 2022-11-21 | 2022-11-25
Financial Sector Supervision | RBS Implementation - Follow-up | Field-Based work - FB | 2023-03-02 | 2023-03-09
Real Sector Statistics | TA - CPI - Updating CPI FY23 | Field-Based work - FB | 2022-11-14 | 2022-11-25
Tax Administration | Strengthening core business functions - Audit (RTAT) | Duty station-based Work - DS | 2022-06-08 | 2022-06-30
Tax Administration | Strengthening human capital -middle managers | Duty station-based Work - DS | 2022-07-01 | 2022-07-28
Tax Administration | HQ-led Post TADAT Assessment Mission | Field-Based work - FB | 2022-07-05 | 2022-07-05
Source: CARTAC

## SVG
CARTAC FY23 Workplan - St Vincent and the Grenadines
Work Program | Activity Name | CD Modality | Start Date | End Date
Customs Administration | Strengthening Performance Management | Duty station-based Work - DS | 2022-05-30 | 2022-06-03
Customs Administration | Developing a Trusted Trader Program | Duty station-based Work - DS | 2022-08-22 | 2022-08-26
Customs Administration | Developing a Trusted Trader Program | Field-Based work - FB | 2023-02-06 | 2023-02-17
External Sector Statistics | BOP/IIP - Improve Source Data | Field-Based work - FB | 2022-09-19 | 2022-09-23
Financial and Fiscal Law | Review of Customs Law | Duty station-based Work - DS | 2022-06-27 | 2022-07-08
Financial and Fiscal Law | Review of Customs Law | Field-Based work - FB | 2022-11-07 | 2022-11-18
Financial Sector Supervision | RBS Implementation across Non-banks-Follow-up Mission-STX | Field-Based work - FB | 2023-03-16 | 2023-03-24
Public Finance Management | Strengthen disaster resilient PFM systems FY23 #cc | Field-Based work - FB | 2022-08-15 | 2023-01-26
Tax Administration | Enhancing Compliance Program | Field-Based work - FB | 2022-05-02 | 2022-05-17
Tax Administration | Support to implementation of a new ICT system | Duty station-based Work - DS | 2022-07-04 | 2022-07-18
Tax Administration | LTX Visit | Field-Based work - FB | 2022-09-05 | 2022-09-09
Source: CARTAC

## Suriname
CARTAC FY23 Workplan - Suriname
Work Program | Activity Name | CD Modality | Start Date | End Date
External Sector Statistics | Suriname-TA-BOP/IIP- Address data gaps | Duty station-based Work - DS | 2023-03-20 | 2023-03-31
Financial and Fiscal Law | Follow Up - Amendment of Central Bank Law (Desk Review) | Duty station-based Work - DS | 2022-05-02 | 2022-06-30
Financial Sector Supervision | Scoping Mission -LTX | Field-Based work - FB | 2022-08-08 | 2022-08-12
Financial Sector Supervision | IFRS 9 and 17 Implementation - Insurance | Field-Based work - FB | 2022-10-12 | 2022-10-21
Financial Stability | SUR CARTAC FY23 Systemic Risk Monitoring LTX | Field-Based work - FB | 2022-05-02 | 2022-05-06
Financial Stability | Suriname-Systemic Risk and Financial Stability | Peer-to-peer engagement - PP | 2022-09-05 | 2022-09-07
Public Finance Management | Mission LTX/STX Support with Chart of Accounts FY23 | Field-Based work - FB | 2022-10-03 | 2022-10-07
Public Finance Management | Mission LTX/STX Strengthen Budget Preparation FY23 | Field-Based work - FB | 2022-10-03 | 2022-10-07
Real Sector Statistics | Suriname - TA - GDP - Improving GDP | Field-Based work - FB | 2022-07-04 | 2022-07-15
Real Sector Statistics | Suriname - TA - RPPI - Developing RPPI | Field-Based work - FB | 2022-09-05 | 2022-09-16
Source: CARTAC

## Trinidad and Tobago
CARTAC FY23 Workplan - Trinidad and Tobago
Work Program | Activity Name | CD Modality | Start Date | End Date
Debt Management | Debt management strategy and annual borrowing plan (mission) | Field-Based work - FB | 2023-01-16 | 2023-01-27
External Sector Statistics | BOP - Address Data Gap in BOP/IIP and Produce CDIS/CPIS Data | Field-Based work - FB | 2023-01-23 | 2023-02-03
Financial and Fiscal Law | Payment System Law Reform | Field-Based work - FB | 2022-07-01 | 2022-07-01
Financial Sector Supervision | TA on Supervisory Practices and Expectations for IRRBB | Duty station-based Work - DS | 2022-07-13 | 2022-07-25
Financial Sector Supervision | Scoping Mission | Field-Based work - FB | 2022-07-25 | 2022-07-29
Financial Sector Supervision | Development of ORSA Guideline and Introductory Workshop on ORSA | Field-Based work - FB | 2022-10-05 | 2022-10-17
Financial Sector Supervision | TA on Market and Liquidity Risk Supervision | Field-Based work - FB | 2022-10-12 | 2022-10-21
Financial Sector Supervision | ORSA Implementation and Supervisory Review Process (Follow-up) | Field-Based work - FB | 2023-01-11 | 2023-01-23
Financial Sector Supervision | TA on Implementation of NSFR | Field-Based work - FB | 2023-03-08 | 2023-03-17
Public Finance Management | Treasury Support Training FY23 PART TWO | Field-Based work - FB | 2022-07-20 | 2022-07-29
Public Finance Management | Strengthening country engagement in PFM reform | Field-Based work - FB | 2022-09-12 | 2022-09-14
Real Sector Statistics | PPI - Updating PPI | Duty station-based Work - DS | 2022-07-11 | 2022-07-22
Tax Administration | Strengthening Core Functions - Audit Program and Capacity | Field-Based work - FB | 2022-07-01 | 2022-07-29
Tax Administration | Strengthening Core Functions - Arrears Management | Field-Based work - FB | 2022-10-03 | 2022-10-27
Tax Administration | LTX Visit | Field-Based work - FB | 2023-02-06 | 2023-02-08
Source: CARTAC

## Turks and Caicos
CARTAC FY23 Workplan - Turks and Caicos
Work Program | Activity Name | CD Modality | Start Date | End Date
Customs Administration | Developing the Training Function | Field-Based work - FB | 2022-05-30 | 2022-06-10
Customs Administration | Developing a Trusted Trader Program (TTP) | Duty station-based Work - DS | 2022-11-28 | 2022-12-02
Customs Administration | Developing the Training Function | Duty station-based Work - DS | 2023-02-13 | 2023-02-17
Customs Administration | Developing a Trusted Trader Program (TTP) | Field-Based work - FB | 2023-03-13 | 2023-03-24
External Sector Statistics | BOP/IIP – Enhance Data Sources | Field-Based work - FB | 2023-01-23 | 2023-02-03
Financial and Fiscal Law | Drafting Legislation to support the establishment of the RA - HYBRID | Field-Based work - FB | 2022-05-09 | 2022-07-29
Financial Sector Supervision | RBS Implementation-Follow-up Mission | Field-Based work - FB | 2022-07-13 | 2022-07-25
Financial Stability | Systemic Risk Monitoring - Peer | Peer-to-peer engagement - PP | 2022-10-03 | 2022-10-05
Financial Stability | Establish FSU_SysRiskMon | Duty station-based Work - DS | 2023-02-06 | 2023-02-10
Financial Stability | Systemic Risk and Financial Stability | Peer-to-peer engagement - PP | 2023-04-24 | 2023-04-26
Macroeconomic Program | Macro-fiscal forecasting | Field-Based work - FB | 2022-05-16 | 2022-05-20
Public Finance Management | Mainstreaming green and gender budgeting FY23 | Field-Based work - FB | 2022-05-12 | 2022-06-03
Real Sector Statistics | TA - RPPI - Updating RPPI | Duty station-based Work - DS | 2022-11-14 | 2022-11-25
Real Sector Statistics | GDP - Improving GDP FY23 | Field-Based work - FB | 2023-03-13 | 2023-03-24
Tax Administration | Organizational Arrangements (Followup - Establishing a Revenue Authority) HYBRID | Field-Based work - FB | 2022-05-09 | 2022-07-29
Tax Administration | LTX Visit | Field-Based work - FB | 2022-06-06 | 2022-06-08
Tax Administration | Organizational Arrangements (Followup - Establishing a Revenue Authority) HYBRID | Field-Based work - FB | 2022-07-25 | 2022-07-29
Tax Administration | Organizational Arrangements (Establishing an RA) | Field-Based work - FB | 2022-09-05 | 2022-09-23
Source: CARTAC

## Regional Training
CARTAC FY23 Workplan - Regional Training
Work Program | Activity Name | CD Modality | Start Date | End Date
Customs Administration | Regional Seminar to Strengthen Performance Management | Interactive learning and workshops - IL | 2022-11-21 | 2022-11-25
Debt Management | Debt management and public-private partnerships (workshop) | Interactive learning and workshops - IL | 2022-06-27 | 2022-07-05
Debt Management | Green bonds (seminar) - #cc | Interactive learning and workshops - IL | 2022-07-12 | 2022-07-13
Debt Management | Gender bonds (seminar) - #gender | Interactive learning and workshops - IL | 2022-07-26 | 2022-07-27
Debt Management | Regional workshop (workshop) | Interactive learning and workshops - IL | 2022-09-05 | 2022-09-16
Debt Management | Regional workshop (workshop) - LTX Horman | Interactive learning and workshops - IL | 2023-03-06 | 2023-03-17
External Sector Statistics | WHD - Training - CARTAC - Remittances | Interactive learning and workshops - IL | 2022-06-27 | 2022-07-01
External Sector Statistics | WHD - Training - CARTAC - ESS - External Sector Statistics - Introductory | Interactive learning and workshops - IL | 2022-10-10 | 2022-10-14
External Sector Statistics | Training - CEMLA - EDS - External Debt Statistics - Introductory | Interactive learning and workshops - IL | 2023-04-17 | 2023-04-21
External Sector Statistics | Training - CEMLA - ESS - BPM6 Update - Advanced | Interactive learning and workshops - IL | 2023-04-24 | 2023-04-28
Financial Sector Supervision | Regional Workshop - Multi-Topics | Interactive learning and workshops - IL | 2022-09-07 | 2022-09-15
Financial Sector Supervision | IFRS 17 Implementation -Follow-up | Interactive learning and workshops - IL | 2022-10-12 | 2022-10-26
Financial Sector Supervision | Review and Assessment of Liquidity and ITG Transactions | Duty station-based Work - DS | 2022-11-09 | 2022-11-23
Financial Sector Supervision | Review and Provide Feedback on Finals Reports of the Working Group | Duty station-based Work - DS | 2023-03-01 | 2023-03-10
Financial Stability | Regional CARTAC FY23 Bank solvency ST | Interactive learning and workshops - IL | 2022-05-23 | 2022-05-27
Financial Stability | Systemic Risk Analysis_FY22_Regional Workshop | Interactive learning and workshops - IL | 2022-10-03 | 2022-10-03
Financial Stability | Risk dashboard | Interactive learning and workshops - IL | 2022-10-03 | 2022-10-07
Financial Stability | Systemic Risk Analysis_FY22_Regional Workshop | Interactive learning and workshops - IL | 2023-01-02 | 2023-01-02
Financial Stability | Regional CARTAC FY22 Climate | Interactive learning and workshops - IL | 2023-02-06 | 2023-02-10
Financial Stability | Regional CARTAC FY23 MaP tools | Interactive learning and workshops - IL | 2023-03-06 | 2023-03-10
Institute for Capacity Development | Macroeconometric Forecasting and Analysis (MFA) - CARTAC | Interactive learning and workshops - IL | 2022-10-24 | 2022-11-04
Institute for Capacity Development | Central Bank Digital Currencies (CBDC) | Interactive learning and workshops - IL | 2023-01-16 | 2023-01-20
Institute for Capacity Development | WHD - Inclusive Growth and Structural Polices - Climate | Interactive learning and workshops - IL | 2023-03-20 | 2023-03-31
Macroeconomic Program | Macroeconomics Webinar Series | Interactive learning and workshops - IL | 2022-05-02 | 2023-04-28
Public Finance Management | Regional IA Remote Workshop - Auditing of Climate Change | Online learning - OL | 2022-05-09 | 2022-05-20
Public Finance Management | Regional IA Remote Workshop - Purchases, payables, payments | Online learning - OL | 2022-10-03 | 2022-10-07
Public Finance Management | Internal Audit Annual Regional Conference | Interactive learning and workshops - IL | 2022-10-31 | 2022-11-04
Real Sector Statistics | Training - NAC - Introduction to measurement of GDP | Interactive learning and workshops - IL | 2022-05-16 | 2022-05-20
Real Sector Statistics | Training - NAC - National Accounts Analysis | Interactive learning and workshops - IL | 2022-05-23 | 2022-05-27
Real Sector Statistics | PFTAC-CARTAC Joint Seminar on National Accounts for Small States | Interactive learning and workshops - IL | 2023-02-13 | 2023-02-17
Real Sector Statistics | CARTAC - Training - NAC - Quality of NAS workshop | Interactive learning and workshops - IL | 2023-02-27 | 2023-03-03
Real Sector Statistics | CARTAC - Training - Improving the Quality of Prices Statistics | Interactive learning and workshops - IL | 2023-03-06 | 2023-03-10
Tax Administration | Regional Workshop - Leadership and Management Development - | Interactive learning and workshops - IL | 2022-05-05 | 2022-05-17
Tax Administration | Report on VAT Policy Framework for Digital Supplies (small importations, digital services, foreign websites) | Duty station-based Work - DS | 2022-05-30 | 2022-09-30
Tax Administration | Roll out of Standardized Audit Guides and Circulars | Interactive learning and workshops - IL | 2022-06-06 | 2022-06-13
Tax Administration | Regional Workshop - Business Continuity and Disaster Preparedness Plan | Interactive learning and workshops - IL | 2022-07-18 | 2022-07-22
Tax Administration | Conduct research with digital service providers | Duty station-based Work - DS | 2022-08-01 | 2022-08-31
Tax Administration | Workshop/ AEOI | Interactive learning and workshops - IL | 2022-08-01 | 2022-08-08
Tax Administration | Workshop risk management | Interactive learning and workshops - IL | 2022-08-12 | 2022-08-12
Tax Administration | VAT for Small Caribbean Jurisdictions: Digital Services and Purchases via Foreign Websites | Interactive learning and workshops - IL | 2022-09-01 | 2022-09-30
Tax Administration | Workshop - Regional Tax Audit Program | Interactive learning and workshops - IL | 2022-10-03 | 2022-10-17
Source: CARTAC